## Sheet1
Date | Start Time | End Time | Total Time | Time (In Minutes) | Description
2019-05-22 | 18:00 | 19:30 | 1 hr 30 min | 90 | Life to Eagle Seminar
2019-06-02 | 15:45 | 17:45 | 2 hr | 120 | Read entire workbook; Wrote first description draft & first impact draft
2019-06-10 | 19:15 | 20:00 | 45 min | 45 | Discuss with Mr. Mac about first description draft & first impact draft
2019-07-16 | 18:30 | 19:30 | 1 hr | 60 | Emails to Family Promise for introduction
2019-08-06 | 15:30 | 16:00 | 30 min | 30 | Call Family Promise and write summary to Mr. Mac
2019-09-10 | 17:30 | 18:00 | 30 min | 30 | Family Promise meeting preparation and agenda creation
2019-09-12 | 16:30 | 20:30 | 4 hr | 240 | Preparation for meeting; Meeting with Family Promise; Discussion Afterward
2019-09-17 | 16:00 | 17:00 | 1 hr | 60 | Typing up notes and thoughts from meeting and writing follow up email
2019-09-23 | 21:00 | 21:30 | 30 min | 30 | Discussing next steps and sketch details; Took video notes
2019-09-25 | 15:30 | 17:00 | 1 hr 30 min | 90 | Writing email to Ms. Mountz about new steps and stages
2019-10-03 | 16:00 | 17:00 | 1 hr | 60 | Drawing first rough sketch
2019-10-07 | 16:00 | 17:15 | 1 hr 15 min | 75 | Writing email to Ms. Mountz with sketch
2019-10-16 | 16:30 | 17:00 | 30 min | 30 | Scheduling second meeting email
2019-10-25 | 20:30 | 21:30 | 1 hr | 60 | Researching TV and tablet connection possibilities
2019-11-04 | 16:30 | 21:00 | 4 hr 30 min | 270 | Preparation; Meeting for locking down details and measurements; Debrief afterwards
2019-11-05 | 17:15 | 18:30 | 1 hr 15 min | 75 | Writing detail confirmation followup email after meeting
2019-11-17 | 19:45 | 21:15 | 1 hr 30 min | 90 | Organizing notes and photos from 11/4 meeting; Research and working on sketchs
2019-11-18 | 16:15 | 17:30 | 1 hr 15 min | 75 | Work on sketches (SketchUp Research, opted for hand drawing)
2019-11-20 | 16:45 | 19:00 | 2 hr 15 min | 135 | Created sketch system; Drew official Sketch #1 (Wall Items); Scanned sketch templates
2019-11-21 | 15:45 | 19:30 | 3 hr 45 min | 225 | Created more sketches; Drew official Sketch #2 (Current Furniture Layout) and working on Sketch #3
2019-11-23 | 16:45 | 19:00 | 2 hr 15 min | 135 | Worked on sketches and scanning
2019-11-24 | 16:30 | 17:45 | 1 hr 15 min | 75 | Finished drawing sketches and scanning
2019-11-27 | 13:45 | 17:45 | 4 hr | 240 | Edited Sketches; Revised workbook summary and impact; Wrote email to Mrs. Mountz w/ sketches
2019-12-02 | 11:45 | 14:00 | 2 hr 15 min | 135 | Wrote back email for meeting scheduling; Worked on materials list; iPad wall mount research
2019-12-05 | 20:45 | 21:45 | 1 hr | 60 | Write back emails; Begin work on presentation; Worked on Workbook
2019-12-07 | 21:45 | 22:45 | 1 hr | 60 | Worked on presentation
2019-12-08 | 20:45 | 21:45 | 1 hr | 60 | Finished first presentation draft
2019-12-09 | 16:30 | 17:45 | 1 hr 15min | 75 | Worked on proposal (materials and tools section, added first images)
2019-12-15 | 17:00 | 18:00 | 1 hr | 60 | Wrote notecards
2019-12-18 | 17:00 | 17:30 | 30 min | 30 | Practice presentation and write back emails
2019-12-19 | 16:00 | 20:30 | 4 hr 30 min | 270 | Preparation; Travel and attending board meeting; Debreif; Email follow-ups; Record keeping
2019-12-20 | 11:30 | 12:30 | 1 hr | 60 | Finished proposal first draft
2019-12-21 | 17:00 | 17:30 | 30 min | 30 | Revised proposal a little and sent to Mr. Mac for review
2019-12-22 | 18:30 | 22:00 | 3 hr 30 min | 210 | Finished proposal second draftt; Wrote back to Mr. Mac; Discussed plan for cable management
2019-12-22 | 12:15 | 12:45 | 30 min | 30 | Respond to proposal next steps email and print vote confirmation
2019-12-26 | 12:30 | 13:30 | 1 hr | 60 | Discussed signatures needed and sent out singnature meeting emails; Met with Mr. Strite & Mr. Maher for signatures
2019-12-27 | 15:00 | 15:30 | 30 min | 30 | Write introduction email to Ms. James
2019-12-28 | 20:30 | 21:30 | 30 min | 30 | Discussed possible donors
2019-12-30 | 10:15 | 10:45 | 30 min | 30 | Travelled to Family Promise for Mrs. Mountz signature
2020-01-06 | 15:45 | 18:30 | 2 hr 45 min | 165 | Revised proposal based on Ms. James suggestions and responed to her email
2020-01-09 | 18:00 | 20:00 | 2 hr | 120 | Prepare and travel to meet with Ms. James; Scanning and emails afterward
2020-01-14 | 19:45 | 21:30 | 1 hr 45 min | 105 | Finished fundraising application and prospective donors list; Scheduled meetings with Mrs. Mountz & Mr. Strite for fundraising application approval
2020-01-15 | 16:30 | 17:30 | 1 hr | 60 | Worked on proposal revisions and project plan
2020-01-16 | 16:45 | 18:00 | 1 hr 15 min | 75 | Travel and meeting with Mrs. Mountz to sign off Fundraising Application
2020-01-18 | 15:45 | 19:45 | 4 hr | 240 | Worked on project plan & shopping list; Discussed technology solution
2020-01-20 | 18:00 | 19:15 | 1 hr 15 min | 75 | Worked on project plan; Got Mr. Strite signature on Fundraising Application
2020-01-21 | 20:00 | 20:45 | 45 min | 45 | Sent emails to Mrs. Mountz & Mr. Franqui
2020-01-22 | 15:45 | 16:15 | 30 min | 30 | Dropped off Fundraising Application for Mr. Franqui signature
2020-01-23 | 16:30 | 16:45 | 15 min | 15 | Pickup of fundraising application
2020-01-29 | 16:00 | 17:45 | 1 hr 45 min | 105 | Almost finished project plan and wrote email to Mrs. Mountz
2020-01-30 | 19:30 | 21:00 | 1 hr 30 min | 90 | Finished project plan and emailed Mr. Mac
2020-02-05 | 17:30 | 18:15 | 45 min | 45 | Wrote follow up to Mrs. Mountz poster number email & work on Mr. Mac project plan revisions
2020-02-07 | 16:30 | 18:30 | 2 hr | 120 | Finished second draft of project plan based on Mr. Mac revisions; Emailed Mr. Mac about revisions and Mrs. Mountz about paint type
2020-02-17 | 12:45 | 13:15 | 30 min | 30 | Set up grandparents meeting and called Ms. Mountz
2020-02-20 | 15:30 | 18:15 | 2 hr 45 min | 165 | Met with grandparents and recieved $100 donation from Lehmans
2020-02-24 | 16:30 | 17:00 | 30 min | 30 | Emailed Mr. Shover, called Pop-Pop
2020-02-26 | 15:30 | 16:45 | 1 hr 15 min | 75 | Preperation and presenting of project to Strauch's; Recieved donation of $150
2020-02-27 | 18:30 | 18:45 | 15 min | 15 | Followed up with Pop-Pop and received a $250 donation
2020-03-02 | 15:30 | 16:15 | 45 min | 45 | Met with Mr. Shover for fundraising, later recieved $200 donation
2020-03-15 | 13:45 | 17:15 | 3 hr 30 min | 210 | Bought all Amazon, Ikea, & Vidabox items; Called Aunt Cindi about meeting; Planned workdays
2020-03-16 | 15:00 | 21:45 | 6 hr 45 min | 405 | Bought remaining items from Best Buy & Home Depot; Called Mrs. Mountz; Tested technology setup
2020-03-17 | 17:00 | 18:30 | 1 hr 30 min | 90 | Met with Mrs. Mountz to find cove base & set up ipad
2020-03-18 | 13:30 | 17:30 | 4 hr | 240 | iPad setup (testing and parental controls); Ordering plaque
2020-03-19 | 12:15 | 18:45 | 6 hr 30 min | 285 | Drilled cable hole and venilation into iPad mount; Dividing up of tasks, reschedule workdays
2020-04-03 | 19:00 | 19:30 | 30 min | 30 | Fundraising video call with Brubakers
2020-05-15 | 19:00 | 19:30 | 30 min | 30 | Discussing workday rescheduled dates
2020-05-16 | 17:00 | 18:00 | 1 hr | 60 | Emailed Mrs. Mountz about Yellow Phase reschedule dates; Read over COVID-19 Business Guidance requirements; Adjusted safety plan in workbook for COVID-19
2020-05-18 | 13:30 | 14:15 | 45 min | 45 | Laid out COVID safety procedures to Mrs. Mountz and discussed job tips posters
2020-05-18 | 20:45 | 22:45 | 2 hr | 60 | Talked over safety plan with Mr. Strite; Recieved feedback from Mr. Snyder; Adjusted workbook safety plan based on Mr. Snyder points
2020-05-19 | 11:30 | 11:45 | 15 min | 15 | Talked to Mrs. Mountz about workday opportunities
2020-05-20 | 15:15 | 16:45 | 1 hr 30 min | 90 | Confirming details with Mrs. Mountz and writing confirmation email to Ms. James
2020-05-21 | 13:30 | 15:30 | 2 hr | 120 | Bought alcohol wipes; Called companies for SDS for hand sanitizer, alcohol wipes, and soap; Revised workbook supplies list
2020-05-22 | 12:45 | 15:00 | 2 hr 15 min | 135 | Called Ms. James for workday safety plan confirmation; Sent out request for adult volunteer; Took inventory of supplies and tools; Refamiliarized with iPad
2020-05-23 | 16:15 | 21:45 | 5 hr 30 min | 330 | Deligated tasks to helpers; Loaded car with materials / tools; Finished posters; Prepared for workday
2020-05-24 | 7:45 | 16:15 | 8 hr 30 min | 510 | Prepared and lead workday 1
2020-05-24 | 21:15 | 23:15 | 2 hr | 120 | Wrapped up details from workday 1 and prepared for workday 2
2020-05-25 | 6:45 | 13:45 | 7 hr | 420 | Prepared and lead workday 2
2020-05-25 | 15:15 | 19:30 | 4 hr 15 min | 255 | Wrapped up details from workday 2 and finished project report first draft
2020-05-26 | 23:15 | 23:45 | 30 min | 30 | Created instruction manual for technology setup
2020-05-27 | 12:15 | 13:00 | 45 min | 45 | Took photos in uniform at site with Mrs. Mountz; Signed press release waver
2020-05-31 | 13:45 | 15:30 | 1 hr 45 min | 105 | Wrote thank you cards to donors; Project report revisions from Mr. Mac
2020-06-01 | 20:00 | 20:45 | 45 min | 45 | Scheduling final sign off meeting
2020-06-02 | 11:00 | 15:45 | 4 hr 45 min | 345 | Revisions to troubleshooting page; Eagle binder put together
2020-06-03 | 15:00 | 15:30 | 30 min | 30 | Final sign off with Mrs. Mountz
TOTAL: | Hours: | 154 | and | Minutes: | 30